## Form B Fees Part A
RFP 599-2013 Form B: Fees Part A
(See B8)
Third Party Contract Administration for the Polo Park Infrastructure Improvements Project RFP No. 599-2013 | Approximate Quantity | Project Role: | Total Person-Hours | Sub-Total Fees | Disbursements | Total Fees Including Disbursements
Name:
Hourly Rate:
(A) Advisory Services - Planning & Preliminary Design Phases
Facilitate and participate in value engineering process/produce a response report | 125 hours
Perform roadway safety audits during Preliminary Design | 100 hours
Review and coordinate responses with the City of Winnipeg to Preliminary Design Report and Drawings | 100 hours
Review Class 3 estimate of costs and cash flow assembled during Project Planning and Preliminary Design | 75 hours
Review/Advise on Monthly reports as they relate to project costs, Change in Works and Change in Services | 50 hours
Undertake independent design checks of various works
Structural / Geotechnical | 25 hours
Roads / Transportation | 75 hours
Drainage | 50 hours
Participate in Public Information Sessions | 25 hours
Provision to the City of a current report on the assignment status on a monthly basis advising of progress, schedule, costs and Change in Services | 75 hours
Subtotal (A) Advisory Services - Planning & Preliminary Design Phases

## Form B Fees Part B
RFP 599-2013 Form B: Fees Part B
(See B8)
Third Party Contract Administration for the Polo Park Infrastructure Improvements Project RFP No. 599-2013 | Approximate Quantity | Project Role: | Total Person-Hours | Sub-Total Fees | Disbursements | Total Fees Including Disbursements
Name:
Hourly Rate:
(B) Advisory Services - Detailed Design, Contract Administration and Post Construction Phases
Facilitate and participate in value engineering process/produce a response report | 100 hours
Perform roadway safety audits during Detailed Design | 75 hours
Review and coordinate responses with the City of Winnipeg to Bid Opportunities and Detailed Design Drawings | 125 hours
Estimated capital costs and cash flow forecasts assembled during Detailed Design | 75 hours
Monthly cost statements and projections for engineering services during Detailed Design | 75 hours
Review/Advise on Monthly reports as they relate to project costs, Change in Works and Change in Services | 75 hours
Review/Advise on Extra work claims and contemplated changes in work | 100 hours
Provision to the City of a current report on the assignment status on a monthly basis advising of progress, schedule, costs and Change in Services | 75 hours
Subtotal (B) - Advisory Services - Detailed Design, Contract Administration and Post Construction Phases
Total Man-Hours
Total Cost of Engineering Services (A) + (B)