## Person hours & Engineering Fees
eFORM P: PERSON HOURS
Person Hours and Estimated Fees
Group Name and Associated Tasks (add Description in each row) |  |  | Summary
| Role/ Project Role: |  | Total Person-Hours | Labour Fees | Allowable Disbursements | Other Disbursements | Total Fees
Name:
Hourly Rate:
Pre-Design Development (PD)
e.g. initiation and set-up
e.g. develop Project Charter, Risk Management Plan, PDP, Stakeholder Analysis
e.g. procure Architectural Design Consultant
e.g. set up project of Cost Control process
e.g. set up Document Management System
Hours
Fees
Design Development (DD)
e.g. oversee Architectural Design Consultant
e.g. provide Progress and Status Reports
e.g. maintain Issue/Decision Logs
e.g. assist with Public & Stakeholder engagement
e.g. maintain Document Management System
Hours
Fees
Contract Documents (CD)
e.g. assist PDO with budget, schedule, quality, risk
e.g. manage all permits
e.g. validate Furniture, Fixtures and Equipment
e.g. assist with review responses at 33%, 66%, 99%, 100%
Hours
Fees
Tendering/Bidding (TB)
e.g. assist in the oversight of the construction tender process and award
Hours
Fees
Contract Administration (CA)
e.g. review Contractor schedule
e.g. lead FF&E planning & management
e.g. review Contractor's Quality Control measures
e.g. provide Risk Management
Hours
Fees
Closeout (CO)
e.g. provide advice for dispute avoidance
e.g. assist with coordination and compilation of O&M manuals, training, warranties, and as-built plans
Hours
Fees
Total Hours
Total % Time Dedicated to Project (as a percentage of total project hours
Total Fees