## FORM B - PRICES
FORM B: PRICES
(SEE B9)
UNIT PRICES
CODE | ITEM | DESCRIPTION | SPEC. | UNIT | APPROX. | UNIT PRICE | AMOUNT
|  |  | REF. |  | QUANTITY
| A | RIVER AVE - OSBORNE ST TO WELLINGTON CRES REHABILITATION
EARTH AND BASE WORKS
A003 | A.1 | Excavation | CW 3110-R22 | m³ | 60 |  | 0
A007 | A.2 | Supplying and Placing Sub-base Material | CW 3110-R22
A007A1 | i) | 50 mm Granular A Limestone |  | tonne | 140 |  | 0
A010 | A.3 | Supplying and Placing Base Course Material | CW 3110-R22
A010A1 | i) | Base Course Material - Granular A Limestone |  | m³ | 150 |  | 0
A012 | A.4 | Grading of Boulevards | CW 3110-R22 | m² | 1500 |  | 0
A014 | A.5 | Boulevard Excavation | CW 3110-R22 | m³ | 60 |  | 0
A022 | A.6 | Geotextile Fabric | CW 3130-R5 |  |  |  | 0
A022A2 | i) | Separation/Filtration Fabric |  | m² | 150 |  | 0
ROADWORKS - REMOVALS/RENEWALS
B001 | A.7 | Pavement Removal | CW 3110-R22
B002 | i) | Concrete Pavement |  | m² | 1300 |  | 0
B004 | A.8 | Slab Replacement | CW 3230-R8
B011 | i) | 200 mm Type 1 Concrete Pavement (Reinforced) |  | m² | 200 |  | 0
B017 | A.9 | Partial Slab Patches | CW 3230-R8
B026 | i) | 200 mm Type 1 Concrete Pavement (Type A) |  | m² | 10 |  | 0
B027 | ii) | 200 mm Type 1 Concrete Pavement (Type B) |  | m² | 200 |  | 0
B029 | iii) | 200 mm Type 1 Concrete Pavement (Type D) |  | m² | 100 |  | 0
B094 | A.10 | Drilled Dowels | CW 3230-R8
B095 | i) | 19.1 mm Diameter |  | each | 500 |  | 0
B097 | A.11 | Drilled Tie Bars | CW 3230-R8
B097A | i) | 15 M Deformed Tie Bar |  | each | 150 |  | 0
B098 | ii) | 20 M Deformed Tie Bar |  | each | 600 |  | 0
B100r | A.12 | Miscellaneous Concrete Slab Removal | CW 3235-R9
B101r | i) | Median Slab |  | m² | 50 |  | 0
B104r | ii) | 100 mm Sidewalk |  | m² | 200 |  | 0
B107i | A.13 | Miscellaneous Concrete Slab Installation | CW 3235-R9
B111i | i) | Type 5 Concrete 100 mm Sidewalk | SD-228A | m² | 130 |  | 0
B114A | A.14 | Type 5 Concrete 100 mm Sidewalk with Block Outs | E13 | m² | 450 |  | 0
| A.15 | Remove and Salvage Existing Paving Stone | CW3330-R5 | m² | 350 |  | 0
| A.16 | Paving Stone Indicator Surfaces - Salvaged Pavers | E14 | m² | 60 |  | 0
| A.17 | Holland Paver, Charcoal Colour | E14 | m² | 10 |  | 0
B114rl | A.18 | Miscellaneous Concrete Slab Renewal | CW 3235-R9
B118rl | i) | 100 mm Type 5 Concrete Sidewalk | SD-228A
B119rl | a) | Less than 5 sq.m. |  | m² | 50 |  | 0
B120rl | b) | 5 sq.m. to 20 sq.m. |  | m² | 200 |  | 0
B121rl | c) | Greater than 20 sq.m. |  | m² | 400 |  | 0
B124 | A.19 | Adjustment of Precast Sidewalk Blocks | CW 3235-R9 | m² | 10 |  | 0
B125 | A.20 | Supply of Precast Sidewalk Blocks | CW 3235-R9 | m² | 5 |  | 0
B125A | A.21 | Removal of Precast Sidewalk Blocks | CW 3235-R9 | m² | 5 |  | 0
B126r | A.22 | Concrete Curb Removal | CW 3240-R10
B127r | i) | Barrier |  | m | 120 |  | 0
B154rl | A.23 | Concrete Curb Renewal | CW 3240-R10
B155rl | i) | Type 1 Concrete Barrier (100 mm reveal ht, Dowelled) Slip Form Paving | SD-205, SD-206A
B155rla2 | a) | 3 m to 30 m |  | m | 200 |  | 0
B155rlb3 | b) | Greater than 30 m |  | m | 400 |  | 0
B189 | A.24 | Regrading Existing Interlocking Paving Stones | CW 3330-R5 | m² | 30 |  | 0
B200 | A.25 | Planing of Pavement | CW 3450-R6
B202 | i) | 50 - 100 mm Depth (Asphalt) |  | m² | 1000 |  | 0
B206 | A.26 | Supply and Install Pavement Repair Fabric | CW 3140-R1 |  |  |  | 0
B206A | i) | Type A |  | m² | 700 |  | 0
B219 | A.27 | Detectable Warning Surface Tiles | CW 3326-R3 | each | 26 |  | 0
| A.28 | Supply and Installation of Directional Bar Tiles | E21 | m | 6 |  | 0
ROADWORKS - NEW CONSTRUCTION
C001 | A.29 | Concrete Pavements, Median Slabs, Bull-noses, and Safety Medians | CW 3310-R18
C008 | i) | Construction of 200 mm Type 1 Concrete Pavement - (Reinforced) |  | m² | 1150 |  | 0
C015 | ii) | Construction of Monolithic Type 1 Concrete Median Slabs | SD-226A | m² | 30 |  | 0
| iii) | Construction of Monolithic Type 1 Concrete 300mm Wide Bike Median Slabs |  | m² | 80 |  | 0
C032 | A.30 | Concrete Curbs, Curb and Gutter, and Splash Strips | CW 3310-R18
C033 | i) | Construction of Barrier (100 mm ht, Type 1, Dowelled) | SD-205 | m | 140 |  | 0
C033A | ii) | Construction of Barrier (150 mm ht, Type 1, Dowelled) | SD-205 | m | 20 |  | 0
C036 | iii) | Construction of Modified Barrier (100 mm ht, Type 1 Dowelled) | SD-203B | m | 110 |  | 0
C046A | iv) | Construction of Curb Ramp (8-12 mm ht, Type 1, Monolithic) | SD-229C | m | 165 |  | 0
C050 | A.31 | Supply and Installation of Dowel Assemblies 19.1mm | CW 3310-R18 | m | 200 |  | 0
C055 | A.32 | Construction of Asphaltic Concrete Pavements | CW 3410-R12
C056 | i) | Main Line Paving
C058 | a) | Type IA |  | tonne | 1150 |  | 0
C059 | ii) | Tie-ins and Approaches
C060 | a) | Type IA |  | tonne | 170 |  | 0
JOINT AND CRACK SEALING
D006 | A.33 | Reflective Crack Maintenance | CW 3250-R7 | m | 500 |  | 0
ASSOCIATED DRAINAGE AND UNDERGROUND WORKS
E003 | A.34 | Catch Basin | CW 2130-R12
E004A | i) | SD-024, 1800 mm deep |  | each | 5 |  | 0
E006 | A.35 | Catch Pit | CW 2130-R12
E007 | i) | SD-023 |  | each | 3 |  | 0
E008 | A.36 | Sewer Service | CW 2130-R12
E009 | i) | 250 mm, PVC
E010 | a) | In a Trench, Class B Sand Bedding, Class 2 Backfill |  | m | 25 |  | 0
E012 | A.37 | Drainage Connection Pipe | CW 2130-R12 | m | 12 |  | 0
E013 | A.38 | Sewer Service Risers | CW 2130-R12
E014 | i) | 250 mm
E016 | a) | SD-015 |  | vert. m | 15 |  | 0
E023 | A.39 | Frames & Covers | CW 3210-R8
E024 | i) | AP-006 - Standard Frame for Manhole and Catch Basin |  | each | 1 |  | 0
E025 | ii) | AP-007 - Standard Solid Cover for Standard Frame |  | each | 1 |  | 0
E028 | iii) | AP-011 - Barrier Curb and Gutter Frame |  | each | 1 |  | 0
E029 | iv) | AP-012 - Barrier Curb and Gutter Cover |  | each | 1 |  | 0
E034 | A.40 | Connecting to Existing Catch Basin | CW 2130-R12
E035 | i) | 250 mm Drainage Connection Pipe |  | each | 3 |  | 0
E036 | A.41 | Connecting to Existing Sewer | CW 2130-R12
E037 | i) | 250 mm (PVC) Connecting Pipe
E040 | a) | Connecting to 450 mm (Conc) Sewer |  | each | 2 |  | 0
E041 | b) | Connecting to 525 mm (Conc) Sewer |  | each | 1 |  | 0
E041B | c) | Connecting to 1350 mm (Brick) Sewer |  | each | 2 |  | 0
| A.42 | Supply and Install Sewer Service Outlet Restrictor | CW 2130-R12, E18
| i) | 150mm |  | each | 2 |  | 0
E046 | A.43 | Removal of Existing Catch Basins | CW 2130-R12 | each | 6 |  | 0
E050 | A.44 | Abandoning Existing Drainage Inlets | CW 2130-R12 | each | 6 |  | 0
ADJUSTMENTS
F001 | A.45 | Adjustment of Manholes/Catch Basins Frames | CW 3210-R8 | each | 5 |  | 0
F002 | A.46 | Replacing Existing Risers | CW 2130-R12
F002A | i) | Pre-cast Concrete Risers |  | vert. m | 1 |  | 0
F003 | A.47 | Lifter Rings (AP-010) | CW 3210-R8
F005 | i) | 51 mm |  | each | 1 |  | 0
F006 | ii) | 64 mm |  | each | 1 |  | 0
F007 | iii) | 76 mm |  | each | 2 |  | 0
F009 | A.48 | Adjustment of Valve Boxes | CW 3210-R8 | each | 20 |  | 0
F010 | A.49 | Valve Box Extensions | CW 3210-R8 | each | 8 |  | 0
F011 | A.50 | Adjustment of Curb Stop Boxes | CW 3210-R8 | each | 4 |  | 0
F018 | A.51 | Curb Stop Extensions | CW 3210-R8 | each | 2 |  | 0
F015 | A.52 | Adjustment of Curb and Gutter Frames | CW 3210-R8 | each | 5 |  | 0
F026 | A.53 | Replacing Existing Flat Top Reducer | CW 2110-R11 | each | 1 |  | 0
LANDSCAPING
G001 | A.54 | Sodding | CW 3510-R9
G002 | i) | width < 600 mm |  | m² | 200 |  | 0
G003 | ii) | width > or = 600 mm |  | m² | 1600 |  | 0
| A.55 | Black Granite Mulch | E22 | m² | 10 |  | 0
MISCELLANEOUS
| A.56 | Transit Piles | DWG P-3565-23 | each | 1 |  | 0
| A.57 | U-Style Bicycle Rack | E25 | each | 10 |  | 0
| A.58 | Supply and Install Polypost | E35 | each | 35 |  | 0
| A.59 | Green Bike Lane Treatment | E19 | m² | 160 |  | 0
| A | RIVER AVE - OSBORNE ST TO WELLINGTON CRES REHABILITATION |  |  |  | Subtotal: | 0
| B | STRADBROOK AVE - WELLINGTON CRES TO OSBORNE ST REHABILITATION
EARTH AND BASE WORKS
A003 | B.1 | Excavation | CW 3110-R22 | m³ | 140 |  | 0
A007 | B.2 | Supplying and Placing Sub-base Material | CW 3110-R22
A007A1 | i) | 50 mm Granular A Limestone |  | tonne | 200 |  | 0
A010 | B.3 | Supplying and Placing Base Course Material | CW 3110-R22
A010A1 | i) | Base Course Material - Granular A Limestone |  | m³ | 120 |  | 0
A012 | B.4 | Grading of Boulevards | CW 3110-R22 | m² | 1700 |  | 0
A014 | B.5 | Boulevard Excavation | CW 3110-R22 | m³ | 20 |  | 0
A022 | B.6 | Geotextile Fabric | CW 3130-R5 |  |  |  | 0
A022A2 | i) | Separation/Filtration Fabric |  | m² | 210 |  | 0
ROADWORKS - REMOVALS/RENEWALS
B001 | B.7 | Pavement Removal | CW 3110-R22
B002 | i) | Concrete Pavement |  | m² | 500 |  | 0
B004 | B.8 | Slab Replacement | CW 3230-R8
B010 | i) | 230 mm Type 1 Concrete Pavement (Plain-Dowelled) |  | m² | 250 |  | 0
B017 | B.9 | Partial Slab Patches | CW 3230-R8
B022 | i) | 230 mm Type 1 Concrete Pavement (Type A) |  | m² | 10 |  | 0
B023 | ii) | 230 mm Type 1 Concrete Pavement (Type B) |  | m² | 250 |  | 0
B025 | iii) | 230 mm Type 1 Concrete Pavement (Type D) |  | m² | 100 |  | 0
B094 | B.10 | Drilled Dowels | CW 3230-R8
B096 | i) | 28.6 mm Diameter |  | each | 700 |  | 0
B097 | B.11 | Drilled Tie Bars | CW 3230-R8
B097A | i) | 15 M Deformed Tie Bar |  | each | 50 |  | 0
B098 | ii) | 20 M Deformed Tie Bar |  | each | 250 |  | 0
B099 | iii) | 25 M Deformed Tie Bar |  | each | 500 |  | 0
B100r | B.12 | Miscellaneous Concrete Slab Removal | CW 3235-R9
B104r | i) | 100 mm Sidewalk |  | m² | 200 |  | 0
B114A | B.13 | Type 5 Concrete 100 mm Sidewalk with Block Outs | E13 | m² | 850 |  | 0
| B.14 | Remove and Salvage Existing Paving Stone | CW3330-R5 | m² | 400 |  | 0
| B.15 | Paving Stone Indicator Surfaces - Salvaged Pavers | E14 | m² | 85 |  | 0
| B.16 | Holland Paver, Charcoal Colour | E14 | m² | 10 |  | 0
B114rl | B.17 | Miscellaneous Concrete Slab Renewal | CW 3235-R9
B118rl | i) | 100 mm Type 5 Concrete Sidewalk | SD-228A
B119rl | a) | Less than 5 sq.m. |  | m² | 50 |  | 0
B120rl | b) | 5 sq.m. to 20 sq.m. |  | m² | 50 |  | 0
B121rl | c) | Greater than 20 sq.m. |  | m² | 300 |  | 0
B124 | B.18 | Adjustment of Precast Sidewalk Blocks | CW 3235-R9 | m² | 10 |  | 0
B125 | B.19 | Supply of Precast Sidewalk Blocks | CW 3235-R9 | m² | 10 |  | 0
B125A | B.20 | Removal of Precast Sidewalk Blocks | CW 3235-R9 | m² | 60 |  | 0
B126r | B.21 | Concrete Curb Removal | CW 3240-R10
B127r | i) | Barrier |  | m | 250 |  | 0
B154rl | B.22 | Concrete Curb Renewal | CW 3240-R10
B155rl | i) | Type 1 Concrete Barrier (100 mm reveal ht, Dowelled) | SD-205, SD-206A
B155rl2 | a) | 3 m to 30 m |  | m | 50 |  | 0
B155rl3 | b) | Greater than 30 m |  | m | 700 |  | 0
B189 | B.23 | Regrading Existing Interlocking Paving Stones | CW 3330-R5 | m² | 40 |  | 0
B200 | B.24 | Planing of Pavement | CW 3450-R6
B202 | i) | 50 - 100 mm Depth (Asphalt) |  | m² | 600 |  | 0
B206 | B.25 | Supply and Install Pavement Repair Fabric | CW 3140-R1 |  |  |  | 0
B206A | i) | Type A |  | m² | 800 |  | 0
B219 | B.26 | Detectable Warning Surface Tiles | CW 3326-R3 | each | 17 |  | 0
| B.27 | Supply and Installation of Directional Bar Tiles | E21 | m | 6 |  | 0
ROADWORKS - NEW CONSTRUCTION
C001 | B.28 | Concrete Pavements, Median Slabs, Bull-noses, and Safety Medians | CW 3310-R18
C007 | i) | Construction of 230 mm Type 1 Concrete Pavement (Plain-Dowelled) |  | m² | 460 |  | 0
C015 | ii) | Construction of Monolithic Type 1 Concrete Median Slabs | SD-226A | m² | 20 |  | 0
| iii) | Construction of Monolithic Type 1 Concrete 300mm Wide Bike Median Slabs |  | m² | 135 |  | 0
C032 | B.29 | Concrete Curbs, Curb and Gutter, and Splash Strips | CW 3310-R18
C033 | i) | Construction of Barrier (100 mm ht, Type 1, Dowelled) | SD-205 | m | 220 |  | 0
C033A | ii) | Construction of Barrier (150 mm ht, Type 1, Dowelled) | SD-205 | m | 10 |  | 0
C036 | iii) | Construction of Modified Barrier (100 mm ht, Type 1 Dowelled) | SD-203B | m | 40 |  | 0
C046A | iv) | Construction of Curb Ramp (8-12 mm ht, Type 1, Monolithic) | SD-229C | m | 65 |  | 0
C050 | B.30 | Supply and Installation of Dowel Assemblies 28.6mm | CW 3310-R18 | m | 100 |  | 0
C055 | B.31 | Construction of Asphaltic Concrete Pavements | CW 3410-R12
C056 | i) | Main Line Paving
C058 | a) | Type IA |  | tonne | 1500 |  | 0
C059 | ii) | Tie-ins and Approaches
C060 | a) | Type IA |  | tonne | 120 |  | 0
JOINT AND CRACK SEALING
D006 | B.32 | Reflective Crack Maintenance | CW 3250-R7 | m | 650 |  | 0
ASSOCIATED DRAINAGE AND UNDERGROUND WORKS
E003 | B.33 | Catch Basin | CW 2130-R12
E004A | i) | SD-024, 1800 mm deep |  | each | 1 |  | 0
E006 | B.34 | Catch Pit | CW 2130-R12
E007 | i) | SD-023 |  | each | 1 |  | 0
E008 | B.35 | Sewer Service | CW 2130-R12
E009 | i) | 250 mm, PVC
E010 | a) | In a Trench, Class B Sand Bedding, Class 2 Backfill |  | m | 4 |  | 0
E012 | B.36 | Drainage Connection Pipe | CW 2130-R12 | m | 3 |  | 0
| B.37 | Sewer Repair - Up to 3.0 Meters Long and Reconnection to 300 CS | CW 2130-R12
| i) | 250 mm - CL60020716
| a) | Class 3 Backfill |  | each | 1 |  | 0
E023 | B.38 | Frames & Covers | CW 3210-R8
E024 | i) | AP-006 - Standard Frame for Manhole and Catch Basin |  | each | 1 |  | 0
E025 | ii) | AP-007 - Standard Solid Cover for Standard Frame |  | each | 1 |  | 0
E028 | iii) | AP-011 - Barrier Curb and Gutter Frame |  | each | 2 |  | 0
E029 | iv) | AP-012 - Barrier Curb and Gutter Cover |  | each | 2 |  | 0
E032 | B.39 | Connecting to Existing Manhole | CW 2130-R12
E033 | i) | 250 mm Catch Basin Lead |  | each | 1 |  | 0
E034 | B.40 | Connecting to Existing Catch Basin | CW 2130-R12
E035 | i) | 250 mm Drainage Connection Pipe |  | each | 1 |  | 0
E046 | B.41 | Removal of Existing Catch Basins | CW 2130-R12 | each | 1 |  | 0
E050 | B.42 | Abandoning Existing Drainage Inlets | CW 2130-R12 | each | 2 |  | 0
ADJUSTMENTS
F001 | B.43 | Adjustment of Manholes/Catch Basins Frames | CW 3210-R8 | each | 7 |  | 0
F002 | B.44 | Replacing Existing Risers | CW 2130-R12
F002A | i) | Pre-cast Concrete Risers |  | vert. m | 1 |  | 0
F003 | B.45 | Lifter Rings (AP-010) | CW 3210-R8
F004 | i) | 38 mm |  | each | 1 |  | 0
F005 | ii) | 51 mm |  | each | 2 |  | 0
F007 | iii) | 76 mm |  | each | 2 |  | 0
F009 | B.46 | Adjustment of Valve Boxes | CW 3210-R8 | each | 12 |  | 0
F010 | B.47 | Valve Box Extensions | CW 3210-R8 | each | 6 |  | 0
F011 | B.48 | Adjustment of Curb Stop Boxes | CW 3210-R8 | each | 4 |  | 0
F018 | B.49 | Curb Stop Extensions | CW 3210-R8 | each | 2 |  | 0
F015 | B.50 | Adjustment of Curb and Gutter Frames | CW 3210-R8 | each | 8 |  | 0
LANDSCAPING
G001 | B.51 | Sodding | CW 3510-R9
G002 | i) | width < 600 mm |  | m² | 300 |  | 0
G003 | ii) | width > or = 600 mm |  | m² | 1800 |  | 0
| B.52 | Tree Removal | E17 | each | 1 |  | 0
| B.53 | Black Granite Mulch | E22 | m² | 20 |  | 0
MISCELLANEOUS
| B.54 | Transit Piles | DWG P-3565-23 | each | 1 |  | 0
| B.55 | Pedestrian Light Relocation | E23 | l.s. | 1 |  | 0
| B.56 | Supply and Install Polypost | E35 | each | 25 |  | 0
| B.57 | Green Bike Lane Treatment | E19 | m² | 70 |  | 0
| B | STRADBROOK AVE - WELLINGTON CRES TO OSBORNE ST REHABILITATION |  |  |  | Subtotal: | 0
| C | WELLINGTON AVE - RIVER AVE TO STRADBROOK AVE REHABILITATION
EARTH AND BASE WORKS
A010 | C.1 | Supplying and Placing Base Course Material | CW 3110-R22
A010A1 | i) | Base Course Material - Granular A Limestone |  | m³ | 80 |  | 0
A012 | C.2 | Grading of Boulevards | CW 3110-R22 | m² | 550 |  | 0
ROADWORKS - REMOVALS/RENEWALS
B001 | C.3 | Pavement Removal | CW 3110-R22
B002 | i) | Concrete Pavement |  | m² | 350 |  | 0
B004 | C.4 | Slab Replacement | CW 3230-R8
B011 | i) | 200 mm Type 1 Concrete Pavement (Reinforced) |  | m² | 150 |  | 0
B017 | C.5 | Partial Slab Patches | CW 3230-R8
B026 | i) | 200 mm Type 1 Concrete Pavement (Type A) |  | m² | 10 |  | 0
B027 | ii) | 200 mm Type 1 Concrete Pavement (Type B) |  | m² | 80 |  | 0
B029 | iii) | 200 mm Type 1 Concrete Pavement (Type D) |  | m² | 150 |  | 0
B094 | C.6 | Drilled Dowels | CW 3230-R8
B095 | i) | 19.1 mm Diameter |  | each | 450 |  | 0
B097 | C.7 | Drilled Tie Bars | CW 3230-R8
B097A | i) | 15 M Deformed Tie Bar |  | each | 50 |  | 0
B098 | ii) | 20 M Deformed Tie Bar |  | each | 550 |  | 0
B100r | C.8 | Miscellaneous Concrete Slab Removal | CW 3235-R9
B104r | i) | 100 mm Sidewalk |  | m² | 80 |  | 0
B114A | C.9 | Type 5 Concrete 100 mm Sidewalk with Block Outs | E13 | m² | 200 |  | 0
| C.10 | Remove and Salvage Existing Paving Stone | CW3330-R5 | m² | 80 |  | 0
| C.11 | Paving Stone Indicator Surfaces - Salvaged Pavers | E14 | m² | 50 |  | 0
| C.12 | Holland Paver, Charcoal Colour | E14 | m² | 30 |  | 0
B114rl | C.13 | Miscellaneous Concrete Slab Renewal | CW 3235-R9
B118rl | i) | 100 mm Type 5 Concrete Sidewalk | SD-228A
B119rl | a) | Less than 5 sq.m. |  | m² | 10 |  | 0
B120rl | b) | 5 sq.m. to 20 sq.m. |  | m² | 50 |  | 0
B121rl | c) | Greater than 20 sq.m. |  | m² | 100 |  | 0
B126r | C.14 | Concrete Curb Removal | CW 3240-R10
B127r | i) | Barrier |  | m | 50 |  | 0
B154rl | C.15 | Concrete Curb Renewal | CW 3240-R10
B155rl | i) | Type 1 Concrete Barrier (100 mm reveal ht, Dowelled) | SD-205, SD-206A
B155rl2 | a) | 3 m to 30 m |  | m | 20 |  | 0
B155rl3 | b) | Greater than 30 m |  | m | 240 |  | 0
B189 | C.16 | Regrading Existing Interlocking Paving Stones | CW 3330-R5 | m² | 20 |  | 0
B200 | C.17 | Planing of Pavement | CW 3450-R6
B202 | i) | 50 - 100 mm Depth (Asphalt) |  | m² | 2800 |  | 0
B206 | C.18 | Supply and Install Pavement Repair Fabric | CW 3140-R1 |  |  |  | 0
B206A | i) | Type A |  | m² | 500 |  | 0
B219 | C.19 | Detectable Warning Surface Tiles | CW 3326-R3 | each | 6 |  | 0
| C.20 | Supply and Installation of Directional Bar Tiles | E21 | m | 6 |  | 0
ROADWORKS - NEW CONSTRUCTION
C001 | C.21 | Concrete Pavements, Median Slabs, Bull-noses, and Safety Medians | CW 3310-R18
C008 | i) | Construction of 200 mm Type 1 Concrete Pavement - (Reinforced) |  | m² | 350 |  | 0
| ii) | Construction of Monolithic Type 1 Concrete 300mm Wide Bike Median Slabs |  | m² | 35 |  | 0
C032 | C.22 | Concrete Curbs, Curb and Gutter, and Splash Strips | CW 3310-R18
C033 | i) | Construction of Barrier (100 mm ht, Type 1, Dowelled) | SD-205 | m | 45 |  | 0
C036 | ii) | Construction of Modified Barrier (100 mm ht, Type 1 Dowelled) | SD-203B | m | 80 |  | 0
C046A | iii) | Construction of Curb Ramp (8-12 mm ht, Type 1, Monolithic) | SD-229C | m | 65 |  | 0
C050 | C.23 | Supply and Installation of Dowel Assemblies 19.1mm | CW 3310-R18 | m | 70 |  | 0
C055 | C.24 | Construction of Asphaltic Concrete Pavements | CW 3410-R12
C056 | i) | Main Line Paving
C058 | a) | Type IA |  | tonne | 700 |  | 0
C059 | ii) | Tie-ins and Approaches
C060 | a) | Type IA |  | tonne | 60 |  | 0
JOINT AND CRACK SEALING
D006 | C.25 | Reflective Crack Maintenance | CW 3250-R7 | m | 300 |  | 0
ASSOCIATED DRAINAGE AND UNDERGROUND WORKS
E003 | C.26 | Catch Basin | CW 2130-R12
E004A | i) | SD-024, 1800 mm deep |  | each | 3 |  | 0
E006 | C.27 | Catch Pit | CW 2130-R12
E007 | i) | SD-023 |  | each | 3 |  | 0
E008 | C.28 | Sewer Service | CW 2130-R12
E009 | i) | 250 mm, PVC
E010 | a) | In a Trench, Class B Sand Bedding, Class 2 Backfill |  | m | 18 |  | 0
E012 | C.29 | Drainage Connection Pipe | CW 2130-R12 | m | 8 |  | 0
E023 | C.30 | Frames & Covers | CW 3210-R8
E024 | i) | AP-006 - Standard Frame for Manhole and Catch Basin |  | each | 2 |  | 0
E025 | ii) | AP-007 - Standard Solid Cover for Standard Frame |  | each | 2 |  | 0
E034 | C.31 | Connecting to Existing Catch Basin | CW 2130-R12
E035 | i) | 250 mm Drainage Connection Pipe |  | each | 3 |  | 0
E036 | C.32 | Connecting to Existing Sewer | CW 2130-R12
E037 | i) | 250 mm (PVC) Connecting Pipe
E039 | a) | Connecting to 375 mm (Conc ) Sewer |  | each | 1 |  | 0
E042 | C.33 | Connecting New Sewer Service to Existing Sewer Service | CW 2130-R12
E043 | i) | 250 mm |  | each | 2 |  | 0
E046 | C.34 | Removal of Existing Catch Basins | CW 2130-R12 | each | 3 |  | 0
E050 | C.35 | Abandoning Existing Drainage Inlets | CW 2130-R12 | each | 7 |  | 0
ADJUSTMENTS
F001 | C.36 | Adjustment of Manholes/Catch Basins Frames | CW 3210-R8 | each | 3 |  | 0
F003 | C.37 | Lifter Rings (AP-010) | CW 3210-R8
F004 | i) | 38 mm |  | each | 1 |  | 0
F005 | ii) | 51 mm |  | each | 2 |  | 0
F007 | iii) | 76 mm |  | each | 2 |  | 0
F009 | C.38 | Adjustment of Valve Boxes | CW 3210-R8 | each | 6 |  | 0
F010 | C.39 | Valve Box Extensions | CW 3210-R8 | each | 3 |  | 0
F011 | C.40 | Adjustment of Curb Stop Boxes | CW 3210-R8 | each | 2 |  | 0
F018 | C.41 | Curb Stop Extensions | CW 3210-R8 | each | 1 |  | 0
LANDSCAPING
G001 | C.42 | Sodding | CW 3510-R9
G002 | i) | width < 600 mm |  | m² | 100 |  | 0
G003 | ii) | width > or = 600 mm |  | m² | 600 |  | 0
| C.43 | Tree Removal | E17 | each | 1 |  | 0
MISCELLANEOUS
| C.44 | Transit Piles | DWG P-3565-23 | each | 1 |  | 0
| C.45 | Supply and Install Polypost | E35 | each | 22 |  | 0
| C | WELLINGTON AVE - RIVER AVE TO STRADBROOK AVE REHABILITATION |  |  |  | Subtotal: | 0
| D | RIVER AVE - HARKNESS AVE TO OSBORNE ST PROTECTED BIKE LANE
EARTH AND BASE WORKS
A003 | D.1 | Excavation | CW 3110-R22 | m³ | 70 |  | 0
A007 | D.2 | Supplying and Placing Sub-base Material | CW 3110-R22
A007A1 | i) | 50 mm Granular A Limestone |  | tonne | 110 |  | 0
A010 | D.3 | Supplying and Placing Base Course Material | CW 3110-R22
A010A1 | i) | Base Course Material - Granular A Limestone |  | m³ | 165 |  | 0
A012 | D.4 | Grading of Boulevards | CW 3110-R22 | m² | 600 |  | 0
A014 | D.5 | Boulevard Excavation | CW 3110-R22 | m³ | 30 |  | 0
A022 | D.6 | Geotextile Fabric | CW 3130-R5 |  |  |  | 0
A022A2 | i) | Separation/Filtration Fabric |  | m² | 125 |  | 0
ROADWORKS - REMOVALS/RENEWALS
B001 | D.7 | Pavement Removal | CW 3110-R22
B002 | i) | Concrete Pavement |  | m² | 250 |  | 0
B017 | D.8 | Partial Slab Patches | CW 3230-R8
B026 | i) | 200 mm Type 1 Concrete Pavement (Type A) |  | m² | 5 |  | 0
B027 | ii) | 200 mm Type 1 Concrete Pavement (Type B) |  | m² | 20 |  | 0
B029 | iii) | 200 mm Type 1 Concrete Pavement (Type D) |  | m² | 30 |  | 0
B094 | D.9 | Drilled Dowels | CW 3230-R8
B095 | i) | 19.1 mm Diameter |  | each | 150 |  | 0
B097 | D.10 | Drilled Tie Bars | CW 3230-R8
B097A | i) | 15 M Deformed Tie Bar |  | each | 150 |  | 0
B098 | ii) | 20 M Deformed Tie Bar |  | each | 250 |  | 0
B100r | D.11 | Miscellaneous Concrete Slab Removal | CW 3235-R9
B101r | i) | Median Slab |  | m² | 50 |  | 0
B104r | ii) | 100 mm Sidewalk |  | m² | 250 |  | 0
B107i | D.12 | Miscellaneous Concrete Slab Installation | CW 3235-R9
B111i | i) | Type 5 Concrete 100 mm Sidewalk | SD-228A | m² | 150 |  | 0
B114A | D.13 | Type 5 Concrete 100 mm Sidewalk with Block Outs | E13 | m² | 1050 |  | 0
| D.14 | Holland Paver, Charcoal Colour | E14 | m² | 50 |  | 0
B114rl | D.15 | Miscellaneous Concrete Slab Renewal | CW 3235-R9
B118rl | i) | 100 mm Type 5 Concrete Sidewalk | SD-228A
B119rl | a) | Less than 5 sq.m. |  | m² | 50 |  | 0
B120rl | b) | 5 sq.m. to 20 sq.m. |  | m² | 150 |  | 0
B121rl | c) | Greater than 20 sq.m. |  | m² | 250 |  | 0
B126r | D.16 | Concrete Curb Removal | CW 3240-R10
B127r | i) | Barrier |  | m | 650 |  | 0
B154rl | D.17 | Concrete Curb Renewal | CW 3240-R10
B155rl | i) | Type 1 Concrete Barrier (100 mm reveal ht, Dowelled) | SD-205, SD-206A
B155rl2 | a) | 3 m to 30 m |  | m | 100 |  | 0
B189 | D.18 | Regrading Existing Interlocking Paving Stones | CW 3330-R5 | m² | 20 |  | 0
| D.19 | Planing of Pavement / Asphalt Removal | CW 3450-R6 , E24
B202 | i) | 50 - 100 mm Depth (Asphalt) |  | m² | 2300 |  | 0
B206 | D.20 | Supply and Install Pavement Repair Fabric | CW 3140-R1 |  |  |  | 0
B206A | i) | Type A |  | m² | 100 |  | 0
B219 | D.21 | Detectable Warning Surface Tiles | CW 3326-R3 | each | 40 |  | 0
| D.22 | Supply and Installation of Directional Bar Tiles | E21 | m | 28 |  | 0
ROADWORKS - NEW CONSTRUCTION
C001 | D.23 | Concrete Pavements, Median Slabs, Bull-noses, and Safety Medians | CW 3310-R18
C008 | i) | Construction of 200 mm Type 1 Concrete Pavement - (Reinforced) |  | m² | 200 |  | 0
C014 | ii) | Construction of Type 1 Concrete Median Slabs | SD-227A | m² | 120 |  | 0
C015 | iii) | Construction of Monolithic Type 1 Concrete Median Slabs | SD-226A | m² | 10 |  | 0
| iv) | Construction of Monolithic Type 1 Concrete 600mm Wide Bike Median Slabs |  | m² | 300 |  | 0
C032 | D.24 | Concrete Curbs, Curb and Gutter, and Splash Strips | CW 3310-R18
C033 | i) | Construction of Barrier (100 mm ht, Type 1, Dowelled) | SD-205 | m | 375 |  | 0
C033A | ii) | Construction of Barrier (150 mm ht, Type 1, Dowelled) | SD-205 | m | 220 |  | 0
C036 | iii) | Construction of Modified Barrier (100 mm ht, Type 1 Dowelled) | SD-203B | m | 50 |  | 0
C046A | iv) | Construction of Curb Ramp (8-12 mm ht, Type 1, Monolithic) | SD-229C | m | 150 |  | 0
C055 | D.25 | Construction of Asphaltic Concrete Pavements | CW 3410-R12
C056 | i) | Raised Bike Lane Paving
C058 | a) | Type IA |  | tonne | 155 |  | 0
C056 | ii) | Main Line Paving
C058 | a) | Type IA |  | tonne | 80 |  | 0
C059 | iii) | Tie-ins and Approaches
C060 | a) | Type IA |  | tonne | 140 |  | 0
JOINT AND CRACK SEALING
D006 | D.26 | Reflective Crack Maintenance | CW 3250-R7 | m | 100 |  | 0
ASSOCIATED DRAINAGE AND UNDERGROUND WORKS
E003 | D.27 | Catch Basin | CW 2130-R12
E004A | i) | SD-024, 1800 mm deep |  | each | 1 |  | 0
E006 | D.28 | Catch Pit | CW 2130-R12
E007 | i) | SD-023 |  | each | 2 |  | 0
E008 | D.29 | Sewer Service | CW 2130-R12
E009 | i) | 250 mm, PVC
E010 | a) | In a Trench, Class B Sand Bedding, Class 2 Backfill |  | m | 4 |  | 0
E012 | D.30 | Drainage Connection Pipe | CW 2130-R12 | m | 10 |  | 0
E013 | D.31 | Sewer Service Risers | CW 2130-R12
E014 | i) | 250 mm
E016 | a) | SD-015 |  | vert. m | 4 |  | 0
E023 | D.32 | Frames & Covers | CW 3210-R8
E024 | i) | AP-006 - Standard Frame for Manhole and Catch Basin |  | each | 2 |  | 0
E025 | ii) | AP-007 - Standard Solid Cover for Standard Frame |  | each | 2 |  | 0
E034 | D.33 | Connecting to Existing Catch Basin | CW 2130-R12
E035 | i) | 250 mm Drainage Connection Pipe |  | each | 2 |  | 0
E036 | D.34 | Connecting to Existing Sewer | CW 2130-R12
E037 | i) | 250 mm (PVC) Connecting Pipe
E041B | a) | Connecting to 1350 mm (Brick) Sewer |  | each | 1 |  | 0
E046 | D.35 | Removal of Existing Catch Basins | CW 2130-R12 | each | 1 |  | 0
E050 | D.36 | Abandoning Existing Drainage Inlets | CW 2130-R12 | each | 3 |  | 0
ADJUSTMENTS
F001 | D.37 | Adjustment of Manholes/Catch Basins Frames | CW 3210-R8 | each | 4 |  | 0
F003 | D.38 | Lifter Rings (AP-010) | CW 3210-R8
F004 | i) | 38 mm |  | each | 2 |  | 0
F005 | ii) | 51 mm |  | each | 4 |  | 0
F009 | D.39 | Adjustment of Valve Boxes | CW 3210-R8 | each | 1 |  | 0
F010 | D.40 | Valve Box Extensions | CW 3210-R8 | each | 1 |  | 0
F011 | D.41 | Adjustment of Curb Stop Boxes | CW 3210-R8 | each | 1 |  | 0
F018 | D.42 | Curb Stop Extensions | CW 3210-R8 | each | 1 |  | 0
LANDSCAPING
G001 | D.43 | Sodding | CW 3510-R9
G002 | i) | width < 600 mm |  | m² | 100 |  | 0
G003 | ii) | width > or = 600 mm |  | m² | 700 |  | 0
| D.44 | Tree Removal | E17 | each | 3 |  | 0
MISCELLANEOUS
| D.45 | Transit Piles | DWG P-3565-23 | each | 3 |  | 0
| D.46 | Supply and Install Polypost | E35 | each | 50 |  | 0
| D.47 | Green Bike Lane Treatment | E19 | m² | 120 |  | 0
| D | RIVER AVE - HARKNESS AVE TO OSBORNE ST PROTECTED BIKE LANE |  |  |  | Subtotal: | 0
| E | STRADBROOK AVE - OSBORNE ST TO HARKNESS AVE PROTECTED BIKE LANE
EARTH AND BASE WORKS
A003 | E.1 | Excavation | CW 3110-R22 | m³ | 220 |  | 0
A007 | E.2 | Supplying and Placing Sub-base Material | CW 3110-R22
A007A1 | i) | 50 mm Granular A Limestone |  | tonne | 220 |  | 0
A010 | E.3 | Supplying and Placing Base Course Material | CW 3110-R22
A010A1 | i) | Base Course Material - Granular A Limestone |  | m³ | 180 |  | 0
A012 | E.4 | Grading of Boulevards | CW 3110-R22 | m² | 600 |  | 0
A022 | E.5 | Geotextile Fabric | CW 3130-R5 |  |  |  | 0
A022A2 | i) | Separation/Filtration Fabric |  | m² | 420 |  | 0
A022A4 | E.6 | Supply and Install Geogrid | CW 3135-R2
A022A5 | i) | Class A Geogrid |  | m² | 370 |  | 0
ROADWORKS - REMOVALS/RENEWALS
B001 | E.7 | Pavement Removal | CW 3110-R22
B002 | i) | Concrete Pavement |  | m² | 70 |  | 0
B004 | E.8 | Slab Replacement | CW 3230-R8
B010 | i) | 230 mm Type 1 Concrete Pavement (Plain-Dowelled) |  | m² | 50 |  | 0
B017 | E.9 | Partial Slab Patches | CW 3230-R8
B022 | i) | 230 mm Type 1 Concrete Pavement (Type A) |  | m² | 5 |  | 0
B023 | ii) | 230 mm Type 1 Concrete Pavement (Type B) |  | m² | 40 |  | 0
B094 | E.10 | Drilled Dowels | CW 3230-R8
B096 | i) | 28.6 mm Diameter |  | each | 180 |  | 0
B097 | E.11 | Drilled Tie Bars | CW 3230-R8
B097A | i) | 15 M Deformed Tie Bar |  | each | 120 |  | 0
B098 | ii) | 20 M Deformed Tie Bar |  | each | 100 |  | 0
B099 | iii) | 25 M Deformed Tie Bar |  | each | 150 |  | 0
B100r | E.12 | Miscellaneous Concrete Slab Removal | CW 3235-R9
B101r | i) | Median Slab |  | m² | 50 |  | 0
B104r | ii) | 100 mm Sidewalk |  | m² | 400 |  | 0
B107i | E.13 | Miscellaneous Concrete Slab Installation | CW 3235-R9
B111i | i) | Type 5 Concrete 100 mm Sidewalk | SD-228A | m² | 280 |  | 0
B114A | E.14 | Type 5 Concrete 100 mm Sidewalk with Block Outs | E13 | m² | 650 |  | 0
| E.15 | Regrading Existing Paving Stone | CW3330-R5 | m² | 50 |  | 0
| E.16 | Holland Paver, Charcoal Colour | E14 | m² | 40 |  | 0
B114rl | E.17 | Miscellaneous Concrete Slab Renewal | CW 3235-R9
B118rl | i) | 100 mm Type 5 Concrete Sidewalk | SD-228A
B119rl | a) | Less than 5 sq.m. |  | m² | 30 |  | 0
B120rl | b) | 5 sq.m. to 20 sq.m. |  | m² | 150 |  | 0
B121rl | c) | Greater than 20 sq.m. |  | m² | 150 |  | 0
B124 | E.18 | Adjustment of Precast Sidewalk Blocks | CW 3235-R9 | m² | 10 |  | 0
B125 | E.19 | Supply of Precast Sidewalk Blocks | CW 3235-R9 | m² | 5 |  | 0
B125A | E.20 | Removal of Precast Sidewalk Blocks | CW 3235-R9 | m² | 20 |  | 0
B126r | E.21 | Concrete Curb Removal | CW 3240-R10
B127r | i) | Barrier |  | m | 520 |  | 0
B154rl | E.22 | Concrete Curb Renewal | CW 3240-R10
B155rl | i) | Type 1 Concrete Barrier (100 mm reveal ht, Dowelled) | SD-205, SD-206A
B155rl2 | a) | 3 m to 30 m |  | m | 50 |  | 0
B155rl3 | b) | Greater than 30 m |  | m | 300 |  | 0
B189 | E.23 | Regrading Existing Interlocking Paving Stones | CW 3330-R5 | m² | 30 |  | 0
| E.24 | Planing of Pavement / Asphalt Removal | CW 3450-R6 , E24
B202 | i) | 50 - 100 mm Depth (Asphalt) |  | m² | 3000 |  | 0
B206 | E.25 | Supply and Install Pavement Repair Fabric | CW 3140-R1 |  |  |  | 0
B206A | i) | Type A |  | m² | 500 |  | 0
B219 | E.26 | Detectable Warning Surface Tiles | CW 3326-R3 | each | 28 |  | 0
| E.27 | Supply and Installation of Directional Bar Tiles | E21 | m | 26 |  | 0
ROADWORKS - NEW CONSTRUCTION
C001 | E.28 | Concrete Pavements, Median Slabs, Bull-noses, and Safety Medians | CW 3310-R18
C007 | i) | Construction of 230 mm Type 1 Concrete Pavement (Plain-Dowelled) |  | m² | 120 |  | 0
C014 | ii) | Construction of Type 1 Concrete Median Slabs | SD-227A | m² | 70 |  | 0
C015 | iii) | Construction of Monolithic Type 1 Concrete Median Slabs | SD-226A | m² | 30 |  | 0
| iv) | Construction of Monolithic Type 1 Concrete 600mm Wide Bike Median Slabs | SD-226A | m² | 210 |  | 0
C032 | E.29 | Concrete Curbs, Curb and Gutter, and Splash Strips | CW 3310-R18
C033 | i) | Construction of Barrier (100 mm ht, Type 1, Dowelled) | SD-205 | m | 360 |  | 0
C033A | ii) | Construction of Barrier (150 mm ht, Type 1, Dowelled) | SD-205 | m | 130 |  | 0
C036 | iii) | Construction of Modified Barrier (100 mm ht, Type 1 Dowelled) | SD-203B | m | 140 |  | 0
C046A | iv) | Construction of Curb Ramp (8-12 mm ht, Type 1, Monolithic) | SD-229C | m | 135 |  | 0
C055 | E.30 | Construction of Asphaltic Concrete Pavements | CW 3410-R12
C056 | i) | Raised Bike Lane Paving
C058 | a) | Type IA |  | tonne | 120 |  | 0
C056 | ii) | Main Line Paving
C058 | a) | Type IA |  | tonne | 360 |  | 0
C059 | iii) | Tie-ins and Approaches
C060 | a) | Type IA |  | tonne | 120 |  | 0
JOINT AND CRACK SEALING
D006 | E.31 | Reflective Crack Maintenance | CW 3250-R7 | m | 200 |  | 0
ASSOCIATED DRAINAGE AND UNDERGROUND WORKS
E003 | E.32 | Catch Basin | CW 2130-R12
E004A | i) | SD-024, 1800 mm deep |  | each | 3 |  | 0
E006 | E.33 | Catch Pit | CW 2130-R12
E007 | i) | SD-023 |  | each | 2 |  | 0
E008 | E.34 | Sewer Service | CW 2130-R12
E009 | i) | 250 mm, PVC
E010 | a) | In a Trench, Class B Sand Bedding, Class 2 Backfill |  | m | 16 |  | 0
E012 | E.35 | Drainage Connection Pipe | CW 2130-R12 | m | 14 |  | 0
E023 | E.36 | Frames & Covers | CW 3210-R8
E024 | i) | AP-006 - Standard Frame for Manhole and Catch Basin |  | each | 2 |  | 0
E025 | ii) | AP-007 - Standard Solid Cover for Standard Frame |  | each | 2 |  | 0
E034 | E.37 | Connecting to Existing Catch Basin | CW 2130-R12
E035 | i) | 250 mm Drainage Connection Pipe |  | each | 2 |  | 0
E036 | E.38 | Connecting to Existing Sewer | CW 2130-R12
E037 | i) | 250 mm (PVC) Connecting Pipe
E038 | a) | Connecting to 300 mm (Conc ) Sewer |  | each | 1 |  | 0
E042 | E.39 | Connecting New Sewer Service to Existing Sewer Service | CW 2130-R12
E043 | i) | 250 mm |  | each | 2 |  | 0
E046 | E.40 | Removal of Existing Catch Basins | CW 2130-R12 | each | 3 |  | 0
E050 | E.41 | Abandoning Existing Drainage Inlets | CW 2130-R12 | each | 1 |  | 0
ADJUSTMENTS
F001 | E.42 | Adjustment of Manholes/Catch Basins Frames | CW 3210-R8 | each | 3 |  | 0
F003 | E.43 | Lifter Rings (AP-010) | CW 3210-R8
F004 | i) | 38 mm |  | each | 1 |  | 0
F005 | ii) | 51 mm |  | each | 1 |  | 0
F009 | E.44 | Adjustment of Valve Boxes | CW 3210-R8 | each | 13 |  | 0
F010 | E.45 | Valve Box Extensions | CW 3210-R8 | each | 7 |  | 0
F011 | E.46 | Adjustment of Curb Stop Boxes | CW 3210-R8 | each | 2 |  | 0
F018 | E.47 | Curb Stop Extensions | CW 3210-R8 | each | 1 |  | 0
F015 | E.48 | Adjustment of Curb and Gutter Frames | CW 3210-R8 | each | 3 |  | 0
LANDSCAPING
G001 | E.49 | Sodding | CW 3510-R9
G002 | i) | width < 600 mm |  | m² | 100 |  | 0
G003 | ii) | width > or = 600 mm |  | m² | 800 |  | 0
| E.50 | Tree Removal | E17 | each | 7 |  | 0
MISCELLANEOUS
| E.51 | Transit Piles | DWG P-3565-23 | each | 3 |  | 0
| E.52 | Supply and Install Polypost | E35 | each | 35 |  | 0
| E | STRADBROOK AVE - OSBORNE ST TO HARKNESS AVE PROTECTED BIKE LANE |  |  |  | Subtotal: | 0
| F | TRAFFIC SIGNALS
RIVER AND LEWIS
| F.1 | Installation of Conduit | CW 3620, E26
| i) | Installation of Conduit - Single |  | m | 35 |  | 0
| F.2 | Installation of Bases | CW 3620, E27 ,E32,E33,E34
| i) | Signal Pole Base – Type G (Light Duty – 32 Dia. Bolts) | SD-313 | each | 2 |  | 0
| F.3 | Ground Rods (Electrodes) | CW 3620 | each | 1 |  | 0
RIVER AND SCOTT
| F.4 | Installation of Conduit | CW 3620, E26
| i) | Installation of Conduit - Single |  | m | 75 |  | 0
| F.5 | Installation of Bases | CW 3620, E27 ,E32,E33,E34
| i) | Signal Pole Base – Type G (Light Duty – 32 Dia. Bolts) | SD-313 | each | 2 |  | 0
| F.6 | Installation of Service Boxes
| i) | Service Box – Pre-Cast (17"x30") | SD-322, E28 | each | 1 |  | 0
| F.7 | Ground Rods (Electrodes) | CW 3620 | each | 1 |  | 0
RIVER AND HARKNESS
| F.8 | Installation of Conduit | CW 3620, E26
| i) | Installation of Conduit - Single |  | m | 10 |  | 0
| F.9 | Installation of Bases | CW 3620, E27 ,E32,E33,E34
| i) | Signal Pole Base – Type G (Light Duty – 32 Dia. Bolts) | SD-313 | each | 1 |  | 0
| F.10 | Removal of Existing Bases and Service Boxes | CW 3620
| i) | Removal of Existing Signal Pole Base or Service Box | CW 3620 | each | 1 |  | 0
| F.11 | Cutovers | CW 3620, E31 | each | 2 |  | 0
RIVER AND NASSAU
| F.12 | Installation of Conduit | CW 3620, E26
| i) | Installation of Conduit - Single |  | m | 275 |  | 0
| ii) | Installation of Conduit - Double |  | m | 220 |  | 0
| F.13 | Installation of Bases | CW 3620, E27 ,E32,E33,E34
| i) | Signal Pole Base – Type A (Light Duty – 25 Dia. Bolts) | SD-310 | each
| ii) | Signal Pole Base – Type G (Light Duty – 32 Dia. Bolts) | SD-313 | each | 9 |  | 0
| iii) | Controller Base | SD-312A | each | 1 |  | 0
| F.14 | Installation of Service Boxes
| i) | Service Box – Pre-Cast (17"x30") | SD-322, E28 | each | 7 |  | 0
| F.15 | Removal of Existing Bases and Service Boxes | CW 3620
| i) | Removal of Existing Signal Pole Base or Service Box | CW 3620 | each | 6 |  | 0
| ii) | Removal of Existing Contoller Base or Pedestal Base | CW 3620 | each | 1 |  | 0
| F.16 | Ground Rods (Electrodes) | CW 3620 | each | 1 |  | 0
| F.17 | Cutovers | CW 3620, E31 | each | 2 |  | 0
RIVER AND OSBORNE
| F.18 | Installation of Conduit | CW 3620, E26
| i) | Installation of Conduit - Single |  | m | 20 |  | 0
| F.19 | Installation of Bases | CW 3620, E27 ,E32,E33,E34
| i) | Signal Pole Base – Type G (Light Duty – 32 Dia. Bolts) | SD-313 | each | 5 |  | 0
| F.20 | Installation of Conduit into Existing Bases | CW 3620
| i) | Installaton of Conduit into Existing Concrete Base | CW 3620 | each | 1 |  | 0
| F.21 | Removal of Existing Bases and Service Boxes | CW 3620
| i) | Removal of Existing Signal Pole Base or Service Box | CW 3620 | each | 3 |  | 0
| F.22 | Cutovers | CW 3620, E31 | each | 5 |  | 0
STRADBROOK AND WELLINGTON
| F.23 | Installation of Conduit | CW 3620, E26
| i) | Installation of Conduit - Single |  | m | 115 |  | 0
| ii) | Installation of Conduit - Double |  | m | 5 |  | 0
| F.24 | Installation of Bases | CW 3620, E27 ,E32,E33,E34
| i) | Signal Pole Base – Type G (Light Duty – 32 Dia. Bolts) | SD-313 | each | 4 |  | 0
| ii) | Pedestal Base | SD-312A | each | 1 |  | 0
| F.25 | Ground Rods (Electrodes) | CW 3620 | each | 1 |  | 0
STRADBROOK AND NASSAU
| F.26 | Installation of Conduit | CW 3620, E26
| i) | Installation of Conduit - Single |  | m | 70 |  | 0
| ii) | Installation of Conduit - Double |  | m | 210 |  | 0
| F.27 | Installation of Bases | CW 3620, E27 ,E32,E33,E34
| i) | Signal Pole Base – Type G (Light Duty – 32 Dia. Bolts) | SD-313 | each | 8 |  | 0
| ii) | Controller Base | SD-312A | each | 1 |  | 0
| F.28 | Installation of Service Boxes
| i) | Service Box – Pre-Cast (17"x30") | SD-322, E28 | each | 4 |  | 0
| F.29 | Removal of Existing Bases and Service Boxes | CW 3620
| i) | Removal of Existing Signal Pole Base or Service Box | CW 3620 | each | 5 |  | 0
| ii) | Removal of Existing Contoller Base or Pedestal Base | CW 3620 | each | 1 |  | 0
| F.30 | Ground Rods (Electrodes) | CW 3620 | each | 1 |  | 0
STRADBROOK AND OSBORNE
| F.31 | Installation of Conduit | CW 3620, E26
| i) | Installation of Conduit - Single |  | m | 30 |  | 0
| ii) | Installation of Conduit - Double |  | m | 5 |  | 0
| F.32 | Installation of Bases | CW 3620, E27 ,E32,E33,E34
| i) | Signal Pole Base – Type G (Light Duty – 32 Dia. Bolts) | SD-313 | each | 1 |  | 0
| ii) | Signal Pole Base - Type OD (Medium Duty – 32 Dia. Bolts) | SD-312A | each | 1 |  | 0
| F.33 | Installation of Service Boxes
| i) | Service Box – Pre-Cast (17"x30") | SD-322, E28 | each | 1 |  | 0
| F.34 | Removal of Existing Bases and Service Boxes | CW 3620
| i) | Removal of Existing Signal Pole Base or Service Box | CW 3620 | each | 2 |  | 0
| F.35 | Ground Rods (Electrodes) | CW 3620 | each | 1 |  | 0
| F.36 | Cutovers | CW 3620, E31 | each | 3 |  | 0
STRADBROOK AND SCOTT
| F.37 | Installation of Conduit | CW 3620, E26
| i) | Installation of Conduit - Single |  | m | 80 |  | 0
| F.38 | Installation of Bases | CW 3620, E27 ,E32,E33,E34
| i) | Signal Pole Base – Type G (Light Duty – 32 Dia. Bolts) | SD-313 | each | 2 |  | 0
| F.39 | Ground Rods (Electrodes) | CW 3620 | each | 1 |  | 0
STRADBROOK AND DONALD
| F.40 | Installation of Conduit | CW 3620, E26
| i) | Installation of Conduit - Single |  | m | 45 |  | 0
| ii) | Installation of Conduit - Double |  | m | 330 |  | 0
| F.41 | Installation of Bases | CW 3620, E27 ,E32,E33,E34
| i) | Signal Pole Base – Type G (Light Duty – 32 Dia. Bolts) | SD-313 | each | 5 |  | 0
| ii) | Signal Pole Base - Type OD (Medium Duty – 32 Dia. Bolts) | SD-312A | each | 3 |  | 0
| iii) | Controller Base | SD-312A | each | 1 |  | 0
| F.42 | Installation of Service Boxes
| i) | Service Box – Pre-Cast (17"x30") | SD-322, E28 | each | 8 |  | 0
| F.43 | Removal of Existing Bases and Service Boxes | CW 3620
| i) | Removal of Existing Signal Pole Base or Service Box | CW 3620 | each | 12 |  | 0
| ii) | Removal of Existing Contoller Base or Pedestal Base | CW 3620 | each | 1 |  | 0
| F.44 | Cutovers | CW 3620, E31 | each | 1 |  | 0
| F | TRAFFIC SIGNALS |  |  |  | Subtotal: | 0
| G | MOBILIZATION /DEMOBILIZATION
I001 | G.1 | Mobilization/Demobilization | E2 | L. sum | 1 |  | 0
| G | MOBILIZATION /DEMOBILIZATION |  |  |  | Subtotal: | 0
SUMMARY
| A | RIVER AVE - OSBORNE ST TO WELLINGTON CRES REHABILITATION |  |  |  | Subtotal: | 0
| B | STRADBROOK AVE - WELLINGTON CRES TO OSBORNE ST REHABILITATION |  |  |  | Subtotal: | 0
| C | WELLINGTON AVE - RIVER AVE TO STRADBROOK AVE REHABILITATION |  |  |  | Subtotal: | 0
| D | RIVER AVE - HARKNESS AVE TO OSBORNE ST PROTECTED BIKE LANE |  |  |  | Subtotal: | 0
| E | STRADBROOK AVE - OSBORNE ST TO HARKNESS AVE PROTECTED BIKE LANE |  |  |  | Subtotal: | 0
| F | TRAFFIC SIGNALS |  |  |  | Subtotal: | 0
| G | MOBILIZATION /DEMOBILIZATION |  |  |  | Subtotal: | 0
| TOTAL BID PRICE (GST extra) (in figures) |  |  |  |  | 0